## Migration checklist
Phase | Task | Owner | Status | Notes / source
Before | Crawl the current site and export every URL (sitemap + crawler) | SEO | To do
Before | Benchmark rankings, clicks and impressions per URL from Search Console (last 90 days) | SEO | To do
Before | Export content: WordPress Tools → Export (WXR/XML: posts, pages, custom post types, comments, custom fields, taxonomies, users) | Dev | To do | Media, themes, plugins and settings are NOT in the export — copy the uploads folder separately
Before | Inventory media, forms, embeds, redirects already in place, and third-party scripts | Dev | To do
Before | Build the one-to-one URL map: every old URL → exactly one new URL | SEO | To do | Google: redirect to the final destination directly; no chains
Before | Decide the new permalink structure and confirm trailing-slash policy | Dev | To do
Before | Set up analytics + Search Console on the new host/domain before launch | SEO | To do
During | Implement server-side permanent redirects (301/308) for every mapped URL | Dev | To do | Google: 301 and other permanent redirects don't cause a loss in PageRank
During | Carry over title tags, meta descriptions, headings, alt text and structured data | SEO | To do
During | Add a self-referencing rel=canonical on every new URL | Dev | To do | Google requirement
During | Update hreflang annotations to the new URLs (if used) | Dev | To do
During | Remove noindex tags and robots.txt blocks from the new site | Dev | To do
During | Update internal links to point at new URLs (not through redirects) | Dev | To do
During | Recreate WordPress-specific URLs: tag/category archives, attachment pages, feeds, paginated pages — redirect or intentionally retire | SEO | To do
During | Test every redirect from the URL map (status code + destination) | QA | To do
During | Test forms, search, embeds and third-party integrations on staging | QA | To do
After | Submit the new sitemap in Search Console | SEO | To do | Google: helps Google learn about the new URLs
After | Use the Change of Address tool only if the domain or subdomain changed | SEO | To do | Not needed for HTTP → HTTPS or same-domain moves
After | Monitor Coverage / Pages report and 404s daily for the first 2 weeks, then weekly | SEO | To do
After | Compare rankings and clicks to the pre-move benchmark at 30, 60 and 90 days | SEO | To do
After | Keep the redirects live for as long as possible, generally at least 1 year | Dev | To do | Google guidance
After | Publish llms.txt and confirm /llms.txt returns 200 (optional, AI discoverability) | Dev | To do
After | Decommission the old WordPress install only after redirects and rankings are verified | Dev | To do

## About
Website migration SEO checklist — Layer3Labs
Source guidance: Google Search Central, 'Site moves with URL changes'; WordPress.org 'Tools Export screen'. Published 2026-09-13.
Companion guide: https://www.layer3labs.io/guides/website-migration-seo-checklist